DOVECOTE NODE3

Virtual Lead Party — Route to Market

Batteries arrive next week. This document is the step-by-step plan to register Dovecote as a UK Virtual Lead Party (VLP) aggregator, start earning Balancing Mechanism revenues immediately via an interim partner, and qualify to trade independently.

| TODAY | Submit G99 fast-track application to SSEN. Contact Octopus Power VPP for interim registration. Start Elexon accession. |
| --- | --- |

| MONTH 1–2 | Complete Elexon BSC accession + KPMG qualification. Register Dovecote as VLP with Host supplier. |
| --- | --- |

| MONTH 3–4 | Go live as Dovecote VLP. Migrate fleet. Begin trading BM independently. Full margin retained. |
| --- | --- |

| TARGET | 20 homes × £1,000–£1,500/yr (BM + Agile) = £20k–£30k/yr fleet revenue = £1,667–£2,500/month |
| --- | --- |

# 1. Why VLP — The Commercial Case

Agile buy/sell arbitrage alone yields ~£350/year per home at 32A DNO limit. The Balancing Mechanism changes the economics entirely.

| Revenue Stream | Per Home / Year | 5 Homes | 20 Homes |
| --- | --- | --- | --- |
| Agile arbitrage only (32A) | £350 | £1,750 | £7,000 |
| + BM via partner aggregator (40–60% share) | £700–£1,000 | £3,500–£5,000 | £14k–£20k |
| + BM as Dovecote VLP (85% share) | £1,000–£1,500 | £5,000–£7,500 | £20k–£30k |
| + Top-performing (>100k/MW/year, own VLP) | £1,200–£2,000 | £6k–£10k | £24k–£40k |

Source: Modo Energy — GB BESS revenues averaged £70k/MW/year in 2025 (range £47k–£88k). Top performers exceeded £100k/MW. Data: modoenergy.com

# 2. Two Parallel Tracks — Run Simultaneously

Do not wait for VLP registration before earning. Both tracks start this week.

| TRACK A | Interim: Register with Octopus Power VPP now. Earning BM revenues within weeks while VLP registration proceeds. |
| --- | --- |

| TRACK B | VLP Registration: Elexon accession + KPMG qualification + Host supplier. 1–4 months. Dovecote earns full margin post-registration. |
| --- | --- |

# 3. Phase-by-Phase Action Plan

| PHASE 0 | DO THIS TODAY | This Week |
| --- | --- | --- |

### Action 1 — G99 Energy Storage Fast-Track Application (SSEN)

Your battery system (10–12kW inverter) is above the default 3.68kW limit and requires G99 registration before grid-connected operation. SSEN has a specific fast-track route for energy storage.

- STEP 1 Download the SSEN G99 Energy Storage Fast-Track form:

- ssen.co.uk — G99 Energy Storage Fast-Track Form

- STEP 2 Complete form with: site address, MPAN, battery kWh capacity, inverter kW rating, proposed export limit.

- STEP 3 Email completed form to: notifications.southmicrogen@sse.com (Central Southern England)

- STEP 4 SSEN target response: 10 working days fast-track. Full G99 if reinforcement required: 45–65 working days.

| NOTE | MCS certification is NOT required for battery-only G99 applications. It IS required if you want Smart Export Guarantee (SEG) payments for solar export. Confirm with your installer. |
| --- | --- |

### Action 2 — Interim VPP Registration: Octopus Power

Octopus manages 2GW of domestic assets through Kraken Flex. They accept home batteries including Fox ESS and Sunsynk-compatible systems. This starts BM revenues within weeks, no regulatory process required on your side.

- Contact Octopus Power commercial team: octopus.energy — ask specifically about battery storage VPP fleet registration

- State clearly: 72kWh per unit, 10–12kW inverter, multiple sites, looking to register as fleet participant

- Ask about revenue share model and minimum fleet size for their current intake

- Also contact Flexitricity (flexitricity.com) — backup option if Octopus lead times are long

### Action 3 — Start Elexon VLP Accession

Email Elexon market entry team to register intent and receive the BSC accession agreement. This starts the clock on the 1–4 month qualification process.

- Email: marketenquiries@elexon.co.uk — subject: “VLP Market Entry — New Applicant”

- State: registering as independent aggregator (Virtual Lead Party) for battery storage fleet

- Request: BSC Accession Agreement and BSCP65 Party Registration Application

- Ask Elexon to schedule initial onboarding call

### Action 4 — Engage a Specialist VLP Consultant

The VLP qualification process involves KPMG technical audits and BSC code compliance. Engage Consulting specialise specifically in this market entry route and will save significant time.

| Engage Consulting | UK specialists in VLP/VTP market entry. They manage the KPMG qualification process, BSC accession, Host supplier negotiation. Essential for first-time applicants. https://www.engage-consulting.co.uk/services/virtual-party-market-entry/ |
| --- | --- |

| PHASE 1 | BATTERIES ARRIVE — COMMISSION & CONNECT | Week 1–2 |
| --- | --- | --- |

### Hardware Commissioning

- 1 Install 3× Nissan e-NV200 battery modules. Confirm BMS integration.

- 2 Install Fox ESS HV10 (10kW) or Sunsynk 12kW inverter. Either supports Agile API + VPP dispatch.

- 3 Confirm half-hourly smart meter in place. This is MANDATORY for BSC settlement. If not present, contact your supplier (Octopus Agile already uses HH metering — confirm MPAN is HH-settled).

- 4 Validate dashboard connectivity — the Node3 portal should be reading live Agile prices and SOC.

- 5 Provide MPAN, site address, installed kW and kWh to both Octopus VPP team and Elexon.

| CRITICAL | Half-hourly settlement is a hard requirement for BSC VLP participation. P483 (August 2025) relaxed some requirements but HH metering at the asset level is still mandatory. Confirm with Octopus before proceeding. |
| --- | --- |

| PHASE 2 | VLP REGISTRATION PROCESS | Months 1–2 |
| --- | --- | --- |

### Step 1 — BSC Accession (Week 1–2 of process)

Elexon sends you the BSC Accession Agreement. This is the formal legal agreement making Dovecote a BSC Party. Sign and return.

- Authorised signatories must be set up in Elexon Kinnect (their customer portal)

- Choose Market Role: Virtual Lead Party (VLP)

- Set target Effective From date — be realistic, allow 8–10 weeks from first contact

### Step 2 — KPMG Qualification Audit (Weeks 3–6)

KPMG conduct the technical qualification on behalf of Elexon. This tests your ability to exchange BSC data correctly. Two qualifications required:

- CVA Qualification (Central Volume Allocation) — proves you can send/receive data with BSC Agents

- SVA Qualification (Supplier Volume Allocation) — confirms understanding of BSC obligations

For the data exchange obligations, use Genstar4 (by Enegen):

| Genstar4 / Enegen | Software specifically built for VLP BSC data obligations. Handles Elexon/NESO data exchange, SBMU management, metering data flows. Essential for a small VLP operator. https://enegen.co.uk/content/generation/Virtual-Lead-Party-VLP-AMVLP.shtml |
| --- | --- |

### Step 3 — Host Supplier Agreement (Weeks 4–8)

As a VLP you need a Host — a licensed electricity supplier who provides the settlement relationship and acts as your Lead Party for BM purposes. Options:

- Octopus Energy — if already partnered on interim VPP, negotiate VLP Host terms

- Limejump (Shell Energy) — established aggregator/host for VLPs

- Ask Engage Consulting for current recommended Host suppliers and commercial terms

| NOTE | The Host takes a small fee or revenue share for the settlement service. Negotiate this carefully — it directly impacts your margin. Typical: 5–15% of BM revenues. |
| --- | --- |

### Step 4 — Register Balancing Mechanism Units (BMUs) (Weeks 6–8)

Each asset (or aggregated portfolio) needs to be registered as a BMU with NESO (National Energy System Operator).

- 1 Register SBMUs (Settlement BM Units) via BSCP15 form or Elexon Kinnect

- 2 Obtain MSID (Metering System ID) pairs for each SBMU

- 3 Register each site's MPAN against the relevant SBMU

- 4 Submit BMU registration to NESO: guidance at neso.energy

| NESO BMU Registration | Registration guide and forms for Balancing Mechanism Units. July 2025 guide available. https://www.neso.energy/document/290631/download |
| --- | --- |

| PHASE 3 | GO LIVE AS DOVECOTE VLP | Month 3–4 |
| --- | --- | --- |

Once BSC accession is complete, KPMG qualification passed, Host agreement signed, and BMUs registered, Dovecote is live as a VLP and can dispatch assets directly into the Balancing Mechanism.

- 1 Migrate fleet from interim partner (Octopus) to Dovecote VLP. Notify Octopus with appropriate notice period.

- 2 Add BM dispatch signal integration to the Node3 dashboard — NESO sends Accept/Reject signals that your system must respond to in near-real-time.

- 3 Set up imbalance management — difference between your offers and actual dispatch must be managed. Genstar4 handles this automatically.

- 4 Begin marketing Dovecote VLP to third-party Node3 operators — other battery owners whose assets you aggregate on your platform.

# 4. G99 Export Upgrade — Is It Worth It?

Current 32A single-phase limit = 7.36kW peak export = 3.68kWh per half-hour slot. Upgrading increases both BM dispatch revenue and Agile arbitrage throughput.

| Connection | Export kW | Est. BM Revenue/yr | SSEN Process |
| --- | --- | --- | --- |
| 32A (current) | 7.36kW | £516/yr | No action needed (G99 fast track only) |
| 50A single-phase | 11.5kW | £805/yr | G99 assessment. £500–£5k. 4–12 weeks. |
| 63A single-phase | 14.5kW | £1,015/yr | G99 assessment + possible reinforcement. |
| 3-phase 32A | 22kW | £1,540/yr | Three-phase connection required. Major work. |

Recommendation: Apply for 50A upgrade alongside the G99 fast-track application. Cost is manageable (£500–£5k depending on substation capacity). If SSEN confirms no reinforcement needed, it's a straightforward approval.

# 5. All Key Contacts

| SSEN G99 (Southern England) | Email fast-track application + energy storage form to this address mailto:notifications.southmicrogen@sse.com |
| --- | --- |

| Elexon Market Entry | Start BSC accession process here. Request VLP market entry pack. https://www.elexon.co.uk/reference/market-entry/market-entry-virtual-lead-party/ |
| --- | --- |

| Engage Consulting | VLP market entry specialists. Commission to manage KPMG qualification + Host negotiation. https://www.engage-consulting.co.uk/services/virtual-party-market-entry/ |
| --- | --- |

| Octopus Power / Kraken Flex | Interim VPP registration. 2GW residential fleet. Fast onboarding. https://octopus.energy |
| --- | --- |

| Habitat Energy | Commercial battery optimisation specialists. 700MW portfolio. Contact for larger fleet deals. https://habitat.energy/contact-us/ |
| --- | --- |

| Flexitricity | Aggregator + BM participant. Backup option for interim VPP. https://www.flexitricity.com |
| --- | --- |

| Genstar4 / Enegen | VLP compliance software — BSC data exchange, SBMU management, imbalance. https://enegen.co.uk/content/generation/Virtual-Lead-Party-VLP-AMVLP.shtml |
| --- | --- |

| NESO (BM Registration) | Register BMUs and get dispatch guidance from National Energy System Operator. https://www.neso.energy/industry-information/connections/help-and-support/use-system-uos-and-virtual-lead-party-vlp |
| --- | --- |

# 6. Timeline at a Glance

| THIS WEEK | Submit G99 fast-track to SSEN • Contact Octopus Power VPP • Email Elexon market entry • Engage consultant |
| --- | --- |
| WEEK 1–2 | Commission Node3 hardware • Confirm HH smart meters • Sign BSC accession agreement • Onboard Octopus VPP (start earning BM revenues) |
| MONTH 1 | KPMG CVA + SVA qualification • Genstar4 software setup • Negotiate Host supplier agreement • Register SBMUs |
| MONTH 2 | MSID allocation • BMU registration with NESO • Final Elexon checks • Test dispatch signalling |
| MONTH 3–4 | DOVECOTE VLP LIVE • Migrate fleet from Octopus • Full BM margin retained • Open platform to third-party Node3 fleet |
| MONTH 6+ | Scale to 20+ homes • Apply G99 50A upgrade per site • £20k–£30k/yr fleet revenue within reach |

This document covers the regulatory route to VLP status as of April 2026. Regulatory frameworks (BSC modifications, Ofgem licensing) are evolving rapidly — verify current requirements with Elexon and Engage Consulting at time of application.